## Übersicht Sonderfreigaben
GWF Sonderfreigabe Tracking 2017 | [12 empty] | 2023-03-16
| SFR-Nr. | PSW (ja/Projekt) | Artikelnummer | Artikelbezeichnung | Lieferanten-Nr | Lieferant | Begründung | Massnahmen | Freigabe bis/ Menge | Verantwortung | Doku | Status | Tracking
1.5 | SFR17-01 | ja | 44.0001 | HRE LSW |  | Escatec Malaysia | Mass 33 kann nicht eingehalten werden | Neues tool | 42916 | Stephan Citteur (SQM) | ok | 20% | freigegeben
1.5 | SFR17-02 | ja | 12.0807 | Body DN20 190mm | 2865012 | Strambini | Masse wurden bei Ersmusterprüfung nicht eingehalten | Anpassung der Kontrollmasse bei Lieferant | nächste Lieferung | Erich Flühler (QM) | ok | 20% | freigegeben
1.5 | SFR17-03 | ja | 12.08 | Flügelrad kpl. Qn 2,5 | 2108001 | Max Allemann | Prüfmass kann nicht eingehalten werden | Anpassung der Zeichnung für Sensus Lieferung | laufend | Erich Flühler (QM) | ok | 20% | freigegeben
1.5 | SFR17-04 | ja | 46.1006 | BGZ Encoder Register AE5 |  | Escatec Malaysia | Abweichung mechanischer Aufbau | Anpassung des Werkzeugs | 43100 | Beata Mendrala (PM) | ok | 50% | freigegeben
1.5 | SFR17-05 | ja | 12.1206 | Steigrohrgehäuse |  | Strambini | Rattermarken auf Dichtflächen | Anpassung des Werkzeugs | 42947 | Erich Flühler (QM) | ok | 50% | freigegeben
1.5 | SFR17-06 | Projekt | closing machine | Closing machine MTK-E | 1322250 | Escatec Malaysia | Closing machine does not preform to spec | GWF will pay rejects till 5% | 43082 | Stephan Citteur (SQM) | ok | n/a | freigegeben
1.5 | SFR17-07 | Projekt | closing machine | Closing machine Resus V8 | 1322250 | Escatec Malaysia | Closing machine does not preform to spec | GWF will pay rejects till 5% | 43082 | Stephan Citteur (SQM) | ok | n/a | freigegeben
1.5 | SFR17-08 | ja | 29.0005 | Schapphaube Rot Unico2 | 2108001 | Allemann | Schnapphaube weisst unsaubere Oberflache | Interne Sonderfreigabe | 43028 | Stephan Citteur (SQM) | fehlt | 100% | freigegeben
1.5 | SFR17-09 | Projekt | 53.000050, 53.000051 | L/P Emitter, L/P Receiver | 1322250 | Escatec Malaysia | Lead time | Visual inspection and critical dimension sampling | Menge: 16000, 20000 | Thomas Frey (R&D) | ok | 100% | freigegeben
1.5 | SFR17-10 | Projekt | 53.000012, 53.000010 | General WHL, Least Sig WHL | 1322250 | Escatec Malaysia | Lead time | Visual inspection and critical dimension sampling | Menge: 72000, 10286 | Thomas Frey (R&D) | ok | 100% | freigegeben
1.5 | SFR17-11 | ja | 44.0001 | General WHL, 1th tool | 1322250 | Escatec Malaysia | Lead time - tool end of life | keine neuen Massnahmen | 2017-11-14 | Ralph Kayser (R&D) | ok | 100% | freigegeben
1.5 | SFR17-12 | ja | 44.000110 | Least Sig WHL - new tool from Supertool | 1322250 | Escatec Malaysia | Lead time | Visual inspection and critical dimension sampling | 2017-12-31 | Ralph Kayser (R&D) | ok | 50% | freigegeben
1.5 | SFR17-13 | ja | 44.0001 | General WHL, 3th tool | 1322250 | Escatec Malaysia | Pre PSW - Lead time | Visual inspection and critical dimension sampling; 1000h module testing at GWF, final tool approval when fully tested and improved | 2017-12-31 | Ralph Kayser (R&D) | ok | 50% | freigegeben
1.5 | SFR17-14 | ja | 44 | Shift Gear | 1322250 | Escatec Malaysia | Pre PSW - Lead time - extension of extisting concession | Visual inspection and critical dimension sampling; 1000h module testing at GWF, final tool approval when fully tested and improved | 2017-12-15 | Ralph Kayser (R&D) | ok | 20% | freigegeben
1.5 | SFR17-15 | Projekt | 53.000012, 53.000010 | General WHL, Least Sig WHL | 1322250 | Escatec Malaysia | Lead time | Visual inspection and critical dimension sampling | Menge: 72000, 10286 | Thomas Frey (R&D) | ok | 100% | freigegeben
1.5 | SFR17-16 | Yes/No | 47.0201 | Encoder Resus V8 | 1322250 | Escatec Malaysia | Cracked sapphire found during assembly | Use MTK-E sapphire press on the Resus V8 assembly line | 4320 pieces | Stephan Citteur (SQM) | fehlt | 0% | freigegeben
1.5 | SFR17-17 | Yes/No | 47.0201 | Encoder Resus V8 | 1322250 | Escatec Malaysia | Ratio Testers malfunctioning and holding up the line | Allow Escatec to pass the 3% reject rate treshold | 2017-12-31 | Stephan Citteur (SQM) | ok | 0% | freigegeben
1.5 | SFR17-18 | Yes/No | 44.000020 | Lower Frame HRE-CH | 1322250 | Escatec Malaysia | Lead time - extension of existing concession | Visual inspection and critical dimension sampling; 1000h module testing at GWF, final tool approval when fully tested and improved | 2017-12-15 | Ralph Kayser (R&D) | ok | 0% | freigegeben
1.5 | SFR17-19 | Yes | 44.0001 | HRE Most Sign. Wheel | 1322250 | Escatec Malaysia | Consession for dimensional deviation | New pin after safety stock | 31.11.2017 | Stephan Citteur (SQM) | ok | 0% | freigegeben
1.5 | SFR17-20 | Projekt | 53.000012, 53.000010 | General WHL, Least Sig WHL | 1322250 | Escatec Malaysia | Lead time | Visual inspection and critical dimension sampling | Menge GW: 72184+72216 Menge LSW: 10177+10183 | Thomas Frey (R&D) | ok | 0% | freigegeben
1.5 | SFR17-21 | Projekt | 53.000012, 53.000011 | General WHL, Least Sig WHL | 1322251 | GWF | Lead time; 0-serial process delayed | Special support in production @ GWF Communication test Visual inspection dial plate | 300 pcs. | Matthias Brokelmann | ok | 0% | freigegeben
1.5 | SFR17-22 | Yes | 44 | HRE Most Light Shield | 1322250 | Escatec Malaysia | Sorting out bad cavities | Sorting | 2017-12-31 | Stephan Citteur (SQM) | ok | 0% | freigegeben
1.5 | SFR17-23 | Yes | 44 | HRE Shift Gear | 1322250 | Escatec Malaysia | Sorting out bad cavities | Sorting | 2017-12-31 | Stephan Citteur (SQM) | ok | 0% | freigegeben
1.5 | SFR17-24 | Yes | 29.0005 | Schnapphaube Rot | 2108001 | Max Allemann | Die Schnapphaube bricht sehr leicht bei den Anspritzpunkten. Ein Änderungsprozess ist schon eingeleitet worden aber wegen dringende Bedarf soll Max Allemann noch mal 3200 Stück von die alte Version fertigen | Fertigen | 3200 pieces | Stephan Citteur (SQM) | ok | 0% | freigegeben
1.5 | SFR17-25 | Yes |  | Kupferbecher Resus V8 | 1322250 | Escatec Malaysia | Alte Kupferbecher haben noch nicht die abgerundete Rand und deswegen gibt es grössere Spänen bei verschliessen. Zirka 34000 Stück sind gesperrt. Die zirka 34000 Stück sollen jetzt aufgebraucht werden. | Nutzung von gesperrte Teilen | 34000 | Matthias Brokelmann (hat das genemigt) | fehlt | 0% | freigegeben
1.5 | SFR17-26 | ja | 44.0001 | General WHL, 3th tool | 1322250 | Escatec Malaysia | Pre PSW - Lead time | Visual inspection and critical dimension sampling; 1000h module testing at GWF, final tool approval when fully tested and improved | 2017-12-31 | Ralph Kayser (R&D) | ok | 0% | freigegeben
1.5 | SFR17-27 |  |  |  | 1322250 | Escatec Malaysia |  |  |  | Stephan Citteur (SQM) | fehlt | 0% | freigegeben
1.5 | SFR17-28 | No |  | LSW Lydia | 1322250 | Escatec Malaysia | Wheel stack does not pass Spinn test. Sorting on cavity number as only cavity 3 is good | Sorting on cavity number | 2017-12-31 | Stephan Citteur (SQM) | fehlt | 0% | freigegeben
1.5 | SFR17-29 | No |  | Sapphire | 1322250 | Escatec Malaysia | Usage of Resus Sapphire instead of MTK-E Sapphire for the last 1200 pcs of | Sampling of 120 pcs and hydraulic testing @GWF to detect improvement/effect of Sapphire | 1200 pcs | Erich Flühler (QM) | ok | 0% | freigegeben
1.5 | SFR17-30 | Ja | 53 | Lydia Lower Frame | 1322251 | Escatec Malaysia | Sorting out bad cavities 2 from Lower Frame Tool | Sortierung | 15000 | Thomas Frey (R&D) | ok | 0% | freigegeben
1.5 | SFR17-31 | Projekt | 53 | Lydia Lower Frame | 1322251 | Escatec Malaysia | The current batch of Lydia Lower Frames was produced with a CPK rate lower than the 1.33 treshold. To be able to make an evaluation of the batch of parts, Escatec made a dimensional inspection with a sample rate of AQL 0.4. No parts with any critical dimension out of specification where found. GWF will release the parts for assembly with this concession. | Rectify tool | 2017-12-31 | Thomas Frey (R&D) | ok
1.5 | SFR17-32 | Projekt | 53 | Lydia Stack Cover | 1322251 | Escatec Malaysia | The current batch of Lydia Stack Covers was produced with a CPK rate lower than the 1.33 treshold. To be able to make an evaluation of the batch of parts, Escatec made a dimensional inspection with a sample rate of AQL 0.4. No parts with any critical dimension out of specification where found. GWF will release the parts for assembly with this concession. | Rectify tool | 2017-12-31 | Thomas Frey (R&D) | ok
1.5 | SFR17-33 | Projekt | 53 | Lydia Bevel Gear Horizontal | 1322251 | Escatec Malaysia | The current batch of Lydia Bevel Gears Horizontal was produced with a CPK rate lower than the 1.33 treshold. To be able to make an evaluation of the batch of parts, Escatec made a dimensional inspection with a sample rate of AQL 0.4. No parts with any critical dimension out of specification where found. GWF will release the parts for assembly with this concession. | Rectify tool | 2017-12-31 | Thomas Frey (R&D) | ok
1.5 | SFR17-34 | Projekt | 53 | Lydia Sweep Hand | 1322251 | Escatec Malaysia | The current batch of Lydia Sweep Hands was produced with a CPK rate lower than the 1.33 treshold. To be able to make an evaluation of the batch of parts, Escatec made a dimensional inspection with a sample rate of AQL 0.4. No parts with any critical dimension out of specification where found. GWF will release the parts for assembly with this concession. | Rectify tool | 2017-12-31 | Thomas Frey (R&D) | ok
| SFR17-35 | Projekt | 53.0001 | Lydia Light Shield | 1322251 | Escatec Malaysia | The current batch of Lydia Light Shields was produced with a CPK rate lower than the 1.33 treshold. To be able to make an evaluation of the batch of parts, Escatec made a dimensional inspection with a sample rate of AQL 0.4. No parts with any critical dimension out of specification where found. GWF will release the parts for assembly with this concession. | Rectify tool | 2017-12-31 | Thomas Frey (R&D) | ok

## Status Liste
Status
offen
freigegeben
abgeschlossen

## Pivot
Zeilenbeschriftungen | Anzahl von SFR-Nr.
Allemann | 1
Escatec Malaysia | 29
GWF | 1
Max Allemann | 2
Strambini | 2
Gesamtergebnis | 35