## 2018_Übersicht Sonderfreigaben
GWF Sonderfreigaben Tracking 2018 | [12 empty] | 2023-03-16
| SFR-Nr. | PSW (Serie/Projekt) | Artikelnummer | Artikelbezeichnung | Lieferanten-Nr | Lieferant | Begründung | Massnahmen | Freigabe bis/ Menge | Verantwortung | Doku | Status | Tracking
1.5 | SFR18-01 | Serie |  |  | 1322250 | Escatec Malaysia | Closing machine IP68 | Keine | 2018-03-31 | Stephan Citteur | ok |  | freigegeben
1.5 | SFR18-02 | Serie |  |  | 1322250 | Escatec Malaysia | Closing machine Resus V8 | Keine | 2018-03-31 | Stephan Citteur | ok |  | freigegeben
1.5 | SFR18-03 | Serie |  |  | 1322250 | Escatec Malaysia | Ratio tester Resus V8 | New software, new dailplate | 2018-03-31 | Stephan Citteur | ok |  | freigegeben
2 | SFR18-04 | Projekt | 53.000012, 53.000010 | General WHL, Least Sig WHL | 1322250 | Escatec Malaysia | Lead time | Visual inspection and critical dimension sampling, Sampling because of scratches hub due to transport | Menge GW: 444000 Menge LSW: 67716 | Thomas Frey (R&D) | ok | freigegeben | abgeschlossen
1.5 | SFR18-05 | Serie | 44.0001 | HRE Number Wheel Most Sig. | 1322250 | Escatec Malaysia | pin gauge 3.02 does not pass | Pin gauge 3.01 temporary accepted, drawing change, tool change, new PSW | 2018-02-28 | Ralph Kayser (R&D) | ok |  | freigegeben
1.5 | SFR18-06 | Serie | 44 | HRE Bevel Gear horizontal | 1322250 | Escatec Malaysia | one cavity not good | sorting out cav. 8, tool rectification | 2018-02-28 | Ralph Kayser (R&D) | ok |  | freigegeben
1.5 | SFR18-07 | Serie | 44 | HRE Most Sig. Light shield | 1322250 | Escatec Malaysia | sorting out no 2 and 3 | tool improvent, PSW | 2018-02-28 | Ralph Kayser (R&D) | ok |  | freigegeben
1.5 | SFR18-08 | Projekt | 44.0001 | HRE Number Wheel general | 1322250 | Escatec Malaysia | New tool. Parts can be used for production because it ist the best option we have. But not yet ready for PSW. | tool improvent, PSW | 2018-02-28 | Ralph Kayser (R&D) | ok |  | freigegeben
2 | SFR18-09 | Projekt | 38.0004 | Shift Gear | 1322250 | Escatec Malaysia | Lead time, open orders of AE3 Encoders | Checking CPK-study for part approval | Menge: 130000pcs | Samuel Hubacher (R&D) | ok |  | abgeschlossen
1.5 | SFR18-10 | Projekt | 44.0001 | HRE Number Whleel Least Sig | 1322250 | Escatec Malaysia | New tool. Parts can be used for production because it ist the best option we have. But not yet ready for PSW. | Frequent cleaning and checks, sorting if necessary, tool improvment ongoing | 2018-03-31 | Ralph Kayser (R&D) | ok |  | freigegeben
0 | SFR18-11 | Projekt | 54 | Resus V8 Gear | GWF | GWF/Escatec Malaysia | 1 Kavität im Werkzeug erzeugt Short Mold | Aussortieren Kavität 4 | 38'980 Stück | Stephan Citteur | ok |  | offen
1.5 | SFR18-12 | Projekt | 44.022 | HRE-CN MTK-E | 1322250 | Escatec Malaysia | High Torque on Encoder Register | Change from Janz Sapphire to BIEG Sapphire | 4140 | Michael Steiman (SCM) | ok |  | freigegeben
2 | SFR18-13 | Projekt | 29.0117 | Body DN20 130mm 1" NPSM/NSF-61 | 2402003 | Gnutti Cirillo SPA | Koaxialität von 0.03 kann im Moment von Gnutti nicht eingehalten werden = 0.1 | Weiter Abklärungen des Lieferanten zur Machbarkeit | 8000 Stück / bis aufgebraucht | Alex Hirt (R&D) | ok / EMPB 1/18 |  | abgeschlossen
2 | SFR18-14 | Projekt | 53.000012/53.000010 | Wheels Lydia | 1322250 | Escatec Malaysia | Escatec needs concession for the wheesl to be able to use these wheels in to production with out a signed PSW for the wheels. | None, known problem, will be solved after tools moved to Escatec and PSW signed | 53.000012: 400000 53.000010: 880000 | Thomas Frey (R&D) | ok |  | abgeschlossen
2 | SFR18-15 | Projekt | 53.000050/53.000051 | Wheels Lydia | 1322250 | Escatec Malaysia | Escatec needs concession for the wheesl to be able to use these wheels in to production with out a signed PSW for the wheels. | None, known problem, will be solved after tools moved to Escatec and PSW signed | 53.000050: 384000 53.000051: 480000 | Thomas Frey (R&D) | ok |  | abgeschlossen
0 | SFR18-16 | Serie | Closing process IP68 | Closing proces IP68 | 1322250 | Escatec Malaysia | The quality of the closing process has a to high reject rate. To keep a normal output of the line, Escatec is allowed to close encoders with a reject rate till 5% | Ongoing improvements on the closing process by GWF | 2018-03-31 | Stephan Citteur | ok |  | offen
0 | SFR18-17 | Serie | Closing process Resus V8 | Closing process Resus V8 | 1322250 | Escatec Malaysia | The quality of the closing process has a to high reject rate. To keep a normal output of the line, Escatec is allowed to close encoders with a reject rate till 5% | Ongoing improvements on the closing process by GWF | 2018-03-31 | Stephan Citteur | ok |  | offen
1.5 | SFR18-18 | Projekt | 20.1069-CT | PCBA Lydia | 1322250 | Escatec Malaysia | A high reject rate was found on the OCD for Lydia caused by bad quality LED and Phototransmitter. Escatec will use only Grade F material from Everlight for production Lydia | Escatec will only purchase Grade F material or higher for future production. | 2018-03-31 | Thomas Frey (R&D) | ok |  | freigegeben
1.5 | SFR18-19 | Serie | Closing process IP68 | Closing process IP68 | 1322250 | Escatec Malaysia | The quality of the closing process has a to high reject rate. To keep a normal output of the line, Escatec is allowed to close encoders with a reject rate till 10% | Ongoing improvements on the closing process by GWF | 2017-03-31 | Stephan Citteur | ok |  | freigegeben
1.5 | SFR18-20 | Serie | Closing process Resus V8 | Closing process Resus V8 | 1322250 | Escatec Malaysia | The quality of the closing process has a to high reject rate. To keep a normal output of the line, Escatec is allowed to close encoders with a reject rate till 10% | Ongoing improvements on the closing process by GWF | 2017-01-31 | Stephan Citteur | ok |  | freigegeben
1.5 | SFR18-21 | Projekt | 44.000075-89 | Dial Plate V8 | 1322250 | Escatec Malaysia | Barcode Print ist noch ungenügend gut für eine PSW aber genügend gut für eine Produktion mit ca. 1-2% rework auf Grund dessen - also handlebar. | ongoing improvments, tests, PSW approval when ready | 60k Stück 31.3.2017 | Ralph Kayser (R&D) | ok |  | freigegeben
1.5 | SFR18-22 | Serie | 29.0843 | Unico3 Hydraulik | 3122602 | Apator | Gehäuse werden ohne Kennzeichnung nach W421 geliefert (wie in der Vergangenheit). Umsetzung nach W421 und MID für Rückverfolgbarkeit noch nicht abgeschlossen bei Apator | continuos discussions with supplier to get it fixed asap | 2'800 Stück 31.01.2018 | Heinz Felix (SCM) | ok |  | freigegeben
2 | SFR18-23 | Serie | 29.0005 | Schnapphaube Rot | 2108001 | Max Allemann | Die Schnapphaube bricht sehr leicht bei den Anspritzpunkten. Ein Änderungsprozess ist schon eingeleitet worden aber wegen dringende Bedarf soll Max Allemann noch mal 5000 Stück von die alte Version fertigen | Fertigen | 5000 pieces | Erich Flühler (QM) | ok | 0% | abgeschlossen
2 | SFR18-24 | Projekt | 29.0118 | Body DN20 130mm 1" NPSM/NSF-61 | 2402003 | Gnutti Cirillo SPA | Koaxialität von 0.03 kann im Moment von Gnutti nicht eingehalten werden = 0.1 | Weiter Abklärungen des Lieferanten zur Machbarkeit | 500 Stück / bis aufgebraucht | Alex Hirt (R&D) | ok / EMPB 2/18 |  | abgeschlossen
2 | SFR18-25 | Projekt | 29.0118 | Body DN15 110mm 3/4" NPSM/NSF-61 | 2402003 | Gnutti Cirillo SPA | Koaxialität von 0.03 kann im Moment von Gnutti nicht eingehalten werden = 0.1 | Weiter Abklärungen des Lieferanten zur Machbarkeit | 500 Stück / bis aufgebraucht | Alex Hirt (R&D) | ok / EMPB 3/18 |  | abgeschlossen
1.5 | SFR18-26 | Serie | 44 | HRE Most Sig. Light shield | 1322250 | Escatec Malaysia | sorting out no 2 and 3 | tool improvent, PSW |  | Thomas Frey (R&D) | ok |  | freigegeben
0 | SFR18-27 | Serie | 44.0001 | MTK-E (HRE-CN), V8 | 1322251 | Escatec Malaysia | Gasket sleeve at the wire location with different cosmetic condition | not defined yet, feedback from MBR needed & decision within R&D regarding next actions | 111150 | Erich Flühler (QM) | ok |  | offen
2 | SFR18-28 | Serie | 47.02 | V8 | 1322252 | Escatec Malaysia | Dimension 27, 28, 29 are out of specification at safequard area after closing procedd | more information from Escatec needed -> Sonderfreigabe gestoppt |  | Erich Flühler (QM) | ok |  | abgeschlossen
1.5 | SFR18-29 | Serie | 53 | Lydia Lower Frame | 1322252 | Escatec Malaysia | Sorting bad cavity | Sorting bad cavity, tool rectification | 2018-04-30 | Stephan Citteur | ok |  | freigegeben
1.5 | SFR18-30 | Serie | 44 | HRE Bevel Gear Horizontal | 1322250 | Escatec Malaysia | Sorting bad cavity | Sorting bad cavity, tool rectification | 31.30.2018 | Stephan Citteur | ok |  | freigegeben
2 | SFR18-31 | Serie | 53.000012/53.000010 | Wheels Lydia | 1322250 | Escatec Malaysia | Material outgasing are causing printing issues. Tool needs to be coated and cleaned in a defined period. | Until rectification, bad printed need to be sorted out. | 53.000012: 400000 53.000010: 880000 | Thomas Frey (R&D) | ok |  | abgeschlossen
1.5 | SFR18-32 | Serie | 12.20061/12.20062 | Steig- und Fallrohrgehäuse | 3106768 | Simofond | Änderungsantrag ist beim SCM liegen geblieben. Es sind noch alte Zähler bei GWF an Lager. Neu-Bestellung verhindern. | Änderungsantrag umsetzen | 12.20061-> 105 12.20062-> 109 | Thomas Vogel (QM) | ok |  | freigegeben
0 | SFR18-33 | Projekt | 44.0001 | HRE Number Wheel general | 1322250 | Escatec Malaysia | New tool. Parts can be used for production because it ist the best option we have. But not yet ready for PSW. | tool improvent, PSW approval until End of April latest | 2018-04-30 | Ralph Kayser (R&D) | ok |  | offen
1.5 | SFR18-34 | Serie | 44 | HRE Most Sig. Light Shield | 132250 | Escatec Malaysia | Sorting and scraping cavity 3 because of flashing | New insert for cavity 3 | 2018-04-13 | Stephan Citteur | ok |  | freigegeben
1.5 | SFR18-35 | Serie | 44.0001 | HRE General wheel | 132250 | Escatec Malaysia | Sorting and scraping cavity 20 & 21 because of excess material and gate insert broken | new gate insert and new air vent pin | 2018-04-04 | Stephan Citteur | ok |  | freigegeben
1.5 | SFR18-36 | Serie | 53 | Lydia Lower Frame | 132250 | Escatec Malaysia | Sorting bad cavity due to broken insert | New solid insert | 2018-03-31 | Stephan Citteur | ok |  | freigegeben
1.5 | SFR18-37 | Serie | 53 | Lydia Lower Frame | 132250 | Escatec Malaysia | Sorting bad cavity due to broken insert | New solid insert | 2018-03-10 | Stephan Citteur | ok |  | freigegeben
1.5 | SFR18-38 | Projekt | 12.2007 | Body DN40 300mm 2" NPSM NSF-61 | 2865012 | Strambini E Boroni | Gewinde M112x2 zur Befestigung des Kopfstück nicht OK = überprüft mit Gewindelehrring | Lieferant Informieren und richtige Gewinde-Bearbeitung anfordern | bis 192 Stk aufgebraucht | Alex Hirt (R&D) | ok / EMPB 7/18 |  | freigegeben
2 | SFR18-39 | Projekt | 29.0117 | Body DN20 130mm 1" NPSM/NSF-61 | 2402003 | Gnutti Cirillo SPA | Koaxialität von 0.03 kann im Moment von Gnutti nicht eingehalten werden = 0.05 | Weiter Abklärungen des Lieferanten zur Machbarkeit | bis 7000 Stück aufgebraucht | Alex Hirt (R&D) | ok |  | abgeschlossen
0 | SFR18-40 | Serie | 29.0005 | Schnapphaube Rot | 2108001 | Max Allemann | Die Schnapphaube bricht sehr leicht bei den Anspritzpunkten. Ein Änderungsprozess ist schon eingeleitet worden aber wegen dringende Bedarf soll Max Allemann noch mal 5000 Stück von die alte Version fertigen | Fertigen | 5000 pieces | Erich Flühler (QM) | ok | 0% | offen
0 | SFR18-41 | Serie | 47.0XXX | Resus V8 Encoder | 132250 | Escatec Malaysia | Closing machine Resus V8 assembly line does not work properly. Escatec can keep producing even if the reject rate goes above the internal threshold | GWF is in the process of commisioning a new design closing machine | 2018-09-30 | Stephan Citteur | ok |  | offen
0 | SFR18-42 | Serie | 44.024X | HRE-CN Encoder | 132250 | Escatec Malaysia | Closing machine for the HRE-CN assembly line does not work properly. Escatec can keep producing even if the reject rate goes above the internal threshold | GWF is in the process of commisioning a new design closing machine | 2018-09-30 | Stephan Citteur | ok |  | offen
0 | SFR18-43 | Serie | 44.0001 | Number Wheel General | 132250 | Escatec Malaysia | Sorting of 2 cavities on 2nd tool Number Wheel General | Tool recititcation till 31.09.2018 | 2400 kpcs | Stephan Citteur | ok |  | offen
0 | SFR18-44 | Serie | 44.0001 | Flat Glass IP68 | 132250 | Escatec Malaysia | Radius at the underside is 0.3 instead of 0.2mm | Concession for 30.000 pieces, next production will be 0.2mm | 30 | Stephan Citteur | ok |  | offen
0 | SFR18-45 | Serie | 44.000029 | HRE Light Shield Most sig. | 132250 | Escatec Malaysia | Flasches at cavity 1 | New insert for cavity 1 | 2015-04-16 | Stephan Citteur | ok |  | offen
0 | SFR18-46 | Serie | 38.01 | Seal Cover neutral Ø9x3.2 | 1322250 | Escatec Malaysia | Flashes on the bottom, Cpk dimension 3.2 OS | Concession for 2880 pcs for CM5 0-series, sort out only flashes | 2880 | Thomas Alder (R&D) | ok |  | offen
0 | SFR18-47 | Serie | 29.084 | Unico3 Hydraulik | 3122602 | Apator | Gehäuse werden ohne Kennzeichnung nach W421 geliefert (wie in der Vergangenheit). Umsetzung nach W421 und MID für Rückverfolgbarkeit noch nicht abgeschlossen bei Apator | continuos discussions with supplier to get it fixed asap | 500 Stück | Heinz Felix (SCM) | ok |  | offen
0 | SFR18-48 | Serie | 44.022 | HRE-CN MTK-E | 1322250 | Escatec Malaysia | High Torque on Encoder Register | Change from Janz Sapphire to BIEG Sapphire | 10000 | Michael Steiman (SCM) | ok |  | offen
0 | SFR18-49 | Serie | 44.XXXXX | HRE-CH | 1322250 | Escatec Malaysia | Problems with sapphires | Will use `Bieg` sapphires in HRE-CH | 2018-05-02 | Erich Flühler (QM) | ok |  | offen
| SFR18-50 | Serie |  |  | 1322250 | Escatec Malaysia | William |  |  | Ralph Kayser (R&D)
| SFR18-51 | Serie | 53.000012/10 | Lydia Wheels | 132250 | Escatec Malaysia | Reject due to spots on wheels which make problems at the printing process | Contact Wision Tools | 2018-07-26 | Stephan Citteur | ok
0 | SFR18-52 | Serie | 44.XXXXX, 42.XXXXX | All registers |  | Janz | Problems with sapphires | Will use `Bieg` sapphires in all registers | 2018-05-02 | Erich Flühler (QM) | ok |  | offen
0 | SFR18-53 | Serie | 44.000029 | HRE Light Shield Most sig. | 132250 | Escatec Malaysia | minor flashes at all cavities | Supertool will make new ejector blades as the old once are worn-out | 2018-05-18 | Stephan Citteur | ok |  | offen
0 | SFR18-54 | Serie | 44 | HRE Light Shield general | 132250 | Escatec Malaysia | Cavity sub inster wear and tear | Sorting for safety stock, tool repair | 2018-09-07 | Stephan Citteur | ok |  | offen
2 | SFR18-55 | Projekt | 46.1 | Frame | 1322250 | Escatec Malaysia | Werkzeug nicht freigegben weil CPK-Studie fehlt und Optimierungen noch offen sind |  | 08.2018/ 20000pcs | Samuel Hubacher (R&D) | ok |  | abgeschlossen
0 | SFR18-56 | Serie | 44 | HRE Shift Gear | 1322250 | Escatec Malaysia | Sorting because chipped Core Insert cavity 15 | Sorting because safety stock | 2018-08-24 | Stephan Citteur | ok |  | offen
1.5 | SFR18-57 | Projekt | 46.1006 | AE5 Encoder | 1322250 | Escatec Malaysia | Produktion von AE5 Encodern ohne unterzeichneten PSW | PO 100-134788, PO 700-134881 wird mit Sonderfreiagbe produziert | 480+720pcs | Samuel Hubacher (R&D) | ok |  | freigegeben
1.5 | SFR18-58 | Projekt | 53.0002 | Lydia Module assembly 1:1 | 1322250 | Escatec Malaysia | 1. No PSW approval for molded part a) Gear SH 1:1 (53.000027) – dimensions 3 and 4 ou of spec – risk assessment attached – low risk b) Bevel Gear vertical 1:1 (53.000026) – part is ok – signed PSW pending c) Bevel Gear horizontal 1:1 (53.000025) – small flash – uncritical area 2. No PSW approval for Finish Product, Lydia Module Assy. 1:1 | Tool rework and resubmission of FAI, cpk and PSW | 540 | Adrian Menczel | ok |  | freigegeben
1.5 | SFR18-59 | Serie | 44.000029 | HRE Light Shield Most sig. | 132250 | Escatec Malaysia | minor flashes at all cavities | New to tool to be made; submission of FAI and cpk results for approval | 2018-09-12 | Adrian Menczel | ok |  | freigegeben
0 | SFR18-60 | Serie | Alle Encoder Zählwerke |  | 132250 | Escatec Malaysia | Wechsel von Short Wire auf Long Wire Phototransistor | vgl. Concession | 2018-08-09 | Michael Steiman (SCM) | ok |  | offen
0 | SFR18-61 | Serie | 46.1006 | AE5 Encoder | 1322250 | Escatec Malaysia | Produktion von AE5 Encodern ohne unterzeichneten PSW | PO 100-135278 / 10200pcs PO 100-135279 / 9600pcs | 10200+9600pcs | Samuel Hubacher (R&D) | ok |  | offen
2 | SFR18-62 | Serie | 46.1020 | CM-5 BGZ (Mbus Mode7) | 1322250 | Escatec Malaysia | Produktion von CM5 Anschlussmodulen mit Silikondichtmasse welche das Ablaufdatum um 2 Monate überschritten hat |  | 2018-11-13 | Samuel Hubacher (R&D) | abgelehnt |  | abgeschlossen
| SFR18-63 | Serie | 44 | Lightpipe HRE | 1322250 | Escatec Malaysia | Extensive flashesa t the lens for cavity 1 | Sorting at Escatec, Sorting at Wisiontool and recitification tool at Wisiontool | 345788 | Stephan Citteur | ok |  | offen
0 | SFR18-64 | Serie | 46.1006 | AE5 Encoder | 1322250 | Escatec Malaysia | Produktion von AE5 Encodern ohne unterzeichneten PSW | PO 100-135887 | 5440pcs | Samuel Hubacher (R&D) | ok |  | offen
0 | SFR18-65 | Projekt | 53.0002 | Lydia Module assembly 1:1 | 1322250 | Escatec Malaysia | 1. No PSW approval for molded part a) Gear SH 1:1 (53.000027) – dimensions 3 and 4 ou of spec – risk assessment attached – low risk b) Bevel Gear vertical 1:1 (53.000026) – part is ok – signed PSW pending c) Bevel Gear horizontal 1:1 (53.000025) – small flash – uncritical area 2. No PSW approval for Finish Product, Lydia Module Assy. 1:1 | Tool rework and resubmission of FAI, cpk and PSW | 1080 | Thomas Frey (R&D) | ok |  | offen
0 | SFR18-66 | Serie | Diverse | Diverse | 2653006 | MIPP GmbH | Zulassung W270 trifft erst im Q4/2018 ein | Sonderfreigabe als interne Bestätigung | Diverse | Michael Steiman (SCM) | ok |  | offen
| SFR18-67 | Serie | 53 | Lydia General Wheel | 1322250 | Escatec Malaysia | Massabweichungen, ohne Freigabe steht Lydia still | Sonderfreigabe für 1.5 million pieces | 1500000 | Stephan Citteur | ok |  | offen
| SFR18-68 | Serie | 44 | HRE Light Shield gerneral | 1322250 | Escatec Malaysia | Sorting for 4 cavities from old tool | New tool with PSW expected in week 44 | week 44 | Stephan Citteur | ok |  | offen
| SFR18-69 | Serie | 44.0004 | HRE Number Wheel general | 1322250 | Escatec Malaysia | Wear and tear all wall plate cavity 21 | Tool rectification week 41 | week 41 | Stephan Citteur | ok |  | offen
| SFR18-70 | Serie | 38.0004 | Shiftgear | 1322250 | Escatec Malaysia | Wear and tear center pin cavity 5 and 6 | Tool rectification with new center pin week 40 | week 40 | Stephan Citteur | ok |  | offen
| SFR18-71 | Serie | 44 | Light Pipe HRE-CH | 1322250 | Escatec Malaysia | Flasches at all cavities | Tool is already repaired, concession for delivered batche only |  | Stephan Citteur | ok |  | offen
| SFR18-72 | Serie | 44 | Shiftgear HRE-CH | 1322250 | Escatec Malaysia | Cavity 11 has gating high and wall dented | Repair Tool | Week 44 | Stephan Citteur | ok |  | offen
| SFR18-73 | Serie | 53.000012/53.000010 | Lydia GW and LSW | 1322250 | Escatec Malaysia | Escatec sees small deviations on Lydia GW and LSW | Measurment analysis by GWF | 1 batch lot | Stephan Citteur | ok |  | offen
| SFR18-74 | Serie | 46.1 | AE5 light Shield | 1322250 | Escatec Malaysia | Flashes on cavity 3 & 4 because of wear and tear, sorting cavity 3 & 4 | Recify the tool on cavity 3 & 4 | week 51 | Stephan Citteur | ok |  | offen
| SFR18-75 | Serie | 53.000010 | Lydia LSW | 1322250 | Escatec Malaysia | Wheels from Wisiontool still not in spec | Wheel evaluation by Thomas Frey | 250000 | Stephan Citteur | ok |  | offen
| SFR18-76 | Serie | 53 | Lydia GW | 1322250 | Escatec Malaysia | Wheels from Wisiontool still not in spec | Wheel evaluation by Thomas Frey | 1600000 | Stephan Citteur | ok |  | offen
| SFR18-77 | Serie | 44 | HRE Light shield general | 1322250 | Escatec Malaysia | Due date for new tool not met | New schedule | week 09 | Stephan Citteur | ok |  | offen
0 | SFR18-66 | Serie | Diverse | Diverse | 2653006 | MIPP GmbH | Zulassung W270 trifft erst im Q4/2018 oder Q1/2019 ein | Sonderfreigabe als interne Bestätigung | Diverse | Michael Steiman (SCM) | ok |  | offen
1.5 | SFR18-79 | Serie | 12.0807 | Body DN20 190mm | 2865012 | Strambini E Boroni | Masse wurden nicht eingehalten | Bearbeitungsprozess optimieren - neue Muster zuschicken | 1200 Stk. | Adrian Menczel | ok |  | freigegeben
1.5 | SFR18-80 | Serie | 53.0001 | Light Pipe |  | Wision | Burrs on light pipe | Tool already rectified. 160k production lot affected. Use as is. | 160k | Adrian Menczel | ok |  | freigegeben
| SFR18-81 | Serie | 03.000076 | Schutzsiebe | 9131170 | Nimoulda | Verzögerung der KTW-Zulassung | Sonderfreigabe auf Serienbestellung während der Übergangsphase | Bis aufgebraucht / 10k | Estin Mathlouthi | ok |  | offen

## Status Liste
Status
offen
freigegeben
abgeschlossen