## 2021_Übersicht QN
GWF Quality Notification Tracking 2021 | [12 empty] | 2023-03-16
| QN-Nr. | PSW (Serie/Projekt) | Artikelnummer | Artikelbezeichnung | Lieferanten-Nr | Lieferant | Begründung | Massnahmen | Freigabe bis/ Menge | Verantwortung | Doku | Status | Tracking
2 | 21-001 | Serie | 53.000012 | Gear G | 1322250 | Escatec | Flashes at pin | Tool repair | N/A | SCI |  |  | abgeschlossen
2 | 21-002 | Serie | 44.0040, 44.0041 | Register V200 SUS | 1322250 | Escatec | Customer request - Counter setting to 0000x | Change request 21001 | N/A | NBO |  |  | abgeschlossen
2 | 21-003 | Serie | 53.000001 | Lower Frame Lydia | 1322250 | Escatec | Dimension 80 out of spec | Use as is | 600K | SCI |  |  | abgeschlossen
2 | 21-004 | Serie | 53.000012 | Lydia General Wheel | 1322250 | Escatec | Dents on wheel | use as is | 200K | SCI |  |  | abgeschlossen
2 | 21-005 | Serie | 44.000028 | HRE Light Shield | 1322250 | Escatec | sub insert broken | Tool repair | N/A | SCI |  |  | abgeschlossen
2 | 21-006 | Serie | 47.000021 | Resus V8 Stack Cover | 1322250 | Escatec | sub insert broken | Tool repair | N/A | SCI |  |  | abgeschlossen
2 | 21-007 | Serie | 53.000010 | Lydia LSW | 1322250 | Escatec | Dents on wheel | Sorting | N/A | SCI |  |  | abgeschlossen
2 | 21-008 | Serie | 44.1550 | Register C700 SUS | 1322250 | Escatec | Gearing not released (FOT part usage) |  | N/A | NBO |  |  | abgeschlossen
2 | 21-009 | Serie | 53.000012 | Lydia General Wheel | 1322250 | Escatec | Measurement differences Escatec - Wisiontool | Use as is | 240K | SCI |  |  | abgeschlossen
2 | 21-010 | Serie | 38.3000 | Opto-Electr. Module ER66 MP | 1322250 | Escatec | Roller priniting nok (space btw. 8.and 9 at Roll1 is too small) | Use as is | 2,4K | SCI |  |  | abgeschlossen
2 | 21-011 | Serie | 53.000012 | Lydia General Wheel | 1322250 | Escatec | Dents on teeth | Use as is | 2500K | SCI |  |  | abgeschlossen
2 | 21-012 | Serie | 53.000010 | Lydia least significant wheel | 1322250 | Escatec | Dents on teeth | Use as is | 500K | SCI |  |  | abgeschlossen
2 | 21-013 | Serie | 29.000331 | Closing Disc |  | Schürholz | New coating specification | Use as is (until new coating is released by GWF) | 11K | JWY |  |  | abgeschlossen
2 | 21-014 | Serie | 53.000001 | Lydia Lower Frame M1 | 1322250 | Escatec | Wear injector blade | Tool repair / concession | 200K | SCI |  |  | abgeschlossen
2 | 21-015 | Serie | 53.000001 | Lydia Lower Frame M2 | 1322250 | Escatec | Broken sub-insert | Tool repair | N/A | SCI |  |  | abgeschlossen
2 | 21-016 | Serie | 44.000119 | Kabel HRE-CH IP68 konfektioniert 5m | 2314040 | Elkalux | Stock shortage at supplier (extended delivery time) | Alternative cable type | 800 | PRU |  |  | abgeschlossen
2 | 21-017 | Serie | 54.000096/97, 54.000174/175 | Gear G, F, H | 1508976 | Janz | Part not in specification | Use as is | N/A | SHU |  |  | abgeschlossen
2 | 21-018 | Serie | 38.200001 | Support R6 | 1322250 | Escatec | Insert broken | Tool repair | N/A | SCI |  |  | abgeschlossen
2 | 21-019 | Serie | 53.000053 | Lydia Shift Gear | 1322250 | Escatec | flashing | Tool repair | N/A | SCI |  |  | abgeschlossen
2 | 21-020 | Project |  |  | 1322250 | Escatec | Purchase order before PSW has been signed | N/A | 10K | SCI |  |  | abgeschlossen
2 | 21-021 | Project |  |  | 1322250 | Escatec | Purchase order before PSW has been signed | N/A | 10K | SCI |  |  | abgeschlossen
2 | 21-022 | Project |  |  | 1322250 | Escatec | Purchase order before PSW has been signed | N/A | 10K | SCI |  |  | abgeschlossen
2 | 21-023 | Project |  |  | 1322250 | Escatec | Purchase order before PSW has been signed | N/A | 10K | SCI |  |  | abgeschlossen
2 | 21-024 | Project |  |  | 1322250 | Escatec | Purchase order before PSW has been signed | N/A | 10K | SCI |  |  | abgeschlossen
0 | 21-025 | Serie | 53.000012 | Lydia General Wheel | 1322250 | Escatec | Dim 4 Kav 14 out of spec | Tool correction Kav 14 dim 4 | 170K | SCI |  |  | offen
0 | 21-026 | Serie | 53.000012 | Lydia General Wheel | 1322250 | Escatec | Dim 4 Kav 14 out of spec | Tool correction Kav 14 dim 4 | 220K | SCI |  |  | offen
0 | 21-027 | Serie | 53.000012 | Lydia General Wheel | 1322250 | Escatec | Dim 4 Kav 14 out of spec | Tool correction Kav 14 dim 4 | 220K | SCI |  |  | offen
0 | 21-029 | Serie | 53.000012 | Lydia General Wheel | 1322250 | Escatec | Dim 4 Kav 14 out of spec | Tool correction Kav 14 dim 4 | 220K | SCI |  |  | offen
0 | 21-030 | Serie | 53.000001 | Lydia Lower Frame | 1322250 | Escatec | Cracked insert cavity 4 | Sorting cavity 4 and tool repair | 30270 | SCI |  |  | offen
0 | 21-031 | Serie | 53.000001 | Lydia Lower Frame | 1322250 | Escatec | Cracked insert cavity 1 | Sorting cavity 1 and tool repair | 30270 | SCI |  |  | offen
0 | 21-032 | Project | 55.000004 | OWG Least Significant Wheel | 1322250 | Escatec | Silver over White instead White over Silver | N/A | 3500 | SCI |  |  | offen
0 | 21-033 | Serie | 53.000010 | Lydia Least Significant Wheel | 1322250 | Escatec | Dim 7 cavity 9 out of spec | Use as is | 200000 | SCI |  |  | offen
0 | 21-034 | Serie | 53.000052 | Lydia Light Shield M2 | 1222350 | Escatec | 2 inserts damaged | Tool repair / sorting | 20000 | SCI |  |  | offen
0 | 21-035 | Serie | 38.000100 | Gear K1 | 1222350 | Escatec | Din 17.6 out of spec by max 0.023mm | Tool adjustment | 18000 | SCI |  |  | offen
0 | 21-036 | Serie | 53.000002 | Lydia Stack Cover | 1222350 | Escatec | Sub-insert broken | Tool repair | N/A | SCI |  |  | offen
0 | 21-037 | Project | 2SE50 | Sonico Edge DN50 | n/a | GWF | Field Test | according to project plan Kassandra | 1 | STH |  |  | offen

## Status Liste
Status
offen
freigegeben
abgeschlossen