## 2026_Übersicht QN
GWF Quality Notification Tracking 2026 | [12 empty] | 2026-10-26
| QN-Nr. | PSW (Serie/Projekt) | Artikelnummer | Artikelbezeichnung | Lieferanten-Nr | Lieferant | Begründung | Massnahmen | Freigabe bis / oder Menge | Verantwortung | Doku | Status | Tracking
26-001
26-002
| 26-003 | Serie | 57.0006 | Electronic register hybrid (ERH) 868MHz | n/a | GWF | An issue has been found to ERH released FW V2.4.7. There are 2.400 devices already manufactured in Escatec with V2.4.7 that we need to rework and ship to EVN + extra 3.600 devices ordered in Escatec with FW version 2.4.12 solving the issue (ordered before STC) | Conditional Release FW version solving the issue and release to production | 6000 | IMA |  | offen | offen
| 26-004 | Serie | 57.0006 | Electronic register hybrid (ERH) 868MHz | n/a | GWF | Temperature calibration issue causing RTC drift | Conitional release only for LoRa configuration | 6000 | IMA |  | offen | offen
0 | 26-005 | Serie | 1F14 | UNICO2compact IP68 NSF | n/a | GWF | Variant UNICO2compact IP68 for US was not enabled in ERP configurator and not released. | Release this version in Konfigurator and make specific Laufkarte for this version only | 1200 | STH |  | offen | offen
0 | 26-006 | Serie | 12.120002/12.120020 | Messeinsatz Unter-/Oberteil Qn 3.5 | 9131170 | Nimoulda | Due to the delay in the release of the new tool, material availability must be ensured. | Produce a small quantity of parts with the old tool to meet customer demand. | 2000 | AZE |  | offen | offen
| 26-007 | Serie | 2235.11020 | Sonico Nano |  | AMS
0 | 26-008 | Serie | 12.160010/12.160011 | Messeinsatz Unter-/Oberteil Qn 6 | 9131170 | Nimoulda | Due to the delay in the release of the new tool, material availability must be ensured. | Produce a small quantity of parts with the old tool to meet customer demand. | 2000 | AZE |  | offen | offen
2 | 26-009 | Serie | 55.000003 | OWG LSW | 1322250 | Escatec | Measurment differences between Wisiontool and Escatec | Fit and function test of OWG with these wheels | 56000 | SCI |  | abgeschlossen | abgeschlossen
0 | 26-010 | Serie | 53.000012 | General Wheels | 9131170 | Nimoulda | M2 tool Qualification | new tool M2 at Nimoulda | 2026-04-30 | TTE |  | offen | offen
0 | 26-011 | Serie | 53.000023 | Lydia Gear | 1322250 | Escatec | venting pin shoulder broken and stuck at sub insert. (Refer the photo below). | tool repair | N/A | TTE |  | offen | offen
0 | 26-012 | Serie | 44.000019 | Protection Lids | 1322250 | Escatec | Flash on location A.B.C | tool repair | N/A | TTE |  | offen | offen
0 | 26-013 | Serie | 47.000020 | Lower Frame V8 | 1322250 | Escatec | Non CTF Dimension (189 A~189 E) OOS issue | tool repair | N/A | TTE |  | offen | offen
0 | 26-014 | Serie | 47.000025 | Lower Bearing Plate V8 | 1322250 | Escatec | Non CTF Dimension (28.1~28.7) near to minimum side. | tool repair | N/A | TTE |  | offen | offen
0 | 26-015 | Serie | 29.002323 | Unico 4-Buchse | 9131170 | Nimoulda | Auf der Unico 4-Buchse 29.002323 aus dem alten Werkzeug/der alten Kavität 1 befindet sich ein zusätzlicher Grat/eine zusätzliche Stufe von 0,13 mm. Es werden dringend 200–300 benötigt bis das neue Werkzeug freigegeben wird. Aus technischer Sicht ist dies akzeptabel. Wir sehen kein Risiko. Danach wird dieses Werkzeug ausgemustert. | Nach der Produktion von 200 -300 Stk./ Kavität 1 wird dieses Werkzeug ausgemustert. | 300 | LKR |  | offen | offen
| 26-016 | Serie | 44.xxxx | Encoder HRE-CH IP68 | 1322250 | Escatec | When applying pressure on glass, the encoder stopts turning | Production stop of water meters with HRE-CH IP68 encoders |  | LKR |  | offen
| 26-017 | Serie | 1F14 | Einstrahl-Wasserzähler UNICO® mit RCM-H200 915 MHz | n/a | Automation Industries Pty Ltd | Wasserzeichenmarkierung „Bleifrei“ (LF) für FA. Automation Industries. Nachbearbeitung des WO00135802/ SO00076062, PO 54796 (530 Stk.) um die Wasserzeichenmarkierung LF nachträglich erstellen. | Nachbearbeitung des WO00135802/ SO00076062, PO 54796 (530 Stk.) um die Wasserzeichenmarkierung LF nachträglich erstellen. | 530 | LKR
| 26-018 | Serie
| 26-019 | Serie
| 26-020 | Serie
| 26-021 | Serie
26-022
26-023
26-024
0 | 26-025 | Serie | 57.0006 | Electronic register hybrid (ERH) 868MHz | n/a | GWF | Release ERH to EVN with known issues open | Conditional release to EVN only after considering risk to release | 2600 | IMA |  | offen | offen
26-026
| 26-027 | Serie | 12.120002/12.120020 | Messeinsatz Unter-/Oberteil Qn 3.5 | 9131170 | Nimoulda | Due to the delay in the release of the new tool, material availability must be ensured. | Produce a small quantity of parts with the old tool to meet customer demand. | 2000 | LKR
26-028
26-029
26-030
26-031
| 26-032 |  | 1F20 | Mehrstrahl-Hauswasserzähler MTK | n/a | n/a | Sonderfreigabe für 0-Serie, SO00083512 |  | 250 | LKR
0 | 26-033 |  | 44.000020-M1 | HRE-CH Lower Frame | 1322250 | Escatec | Ein Einsatz ist kaputt. An den Teilen fehlt ein Loch. Werkzeug anhalten bis zur Reparatur. |  |  | STI |  | offen | offen
| 26-034 | Serie | 44.1XXX | Nutzung Resus V8 Bevel Gear vertical in HRE-CH | 1322250 | Escatec | Niederigere Widerstand mit diese Bevel Gear | Tool repair | 6524 | SCI
| 26-035 | Serie | 44.1XXX | Nutzung Resus V8 Lower Frame in HRE-CH | 1322250 | Escatec | HRE-CH Lower Frame tool is broken, so we need to use Resus V8 Lower Frame to be able to continue our production | Tool repair | 30000 | SCI
| 26-036 |  | 1F16 V000029748 1F16 V000029749
| 26-037 |  | 46.100006 | GWF AE5 Light Shield | 1322250 | Escatec |  | Part has flash issue at Cav 1,2,3,4, |  | STI |  | Open
| 26-038 | Serie | 53.000002 | Lydia Stack Cover M2 | 1322250 | Escatec | Cav 8 has shining surface on produce part. | tool repair | 150000 | TTE |  | Open
| 26-040 | Serie | 30.3001 | GND-Kontaktplatte |  | Bohao Prototype Manufacturing Co., Limited | Maße (13, 15 und 21) außerhalb der Toleranzen. |  | 500 | LKR
| 26-041 | Serie | 47.000115 | HRE-CH IP68, Jroyal coppe cup instead of Oshiba copper cup | 1322250 | Escatec | The Oshiba copper cups in stock at Escatec are NOK | Use Jroyal copper cup | 10000 | SCI
| 26-042 | Serie | 47.000020 | V8 Lower Frame |  | Escatec | Flash on different spots. | Tool stop and repair |  | STI |  | Open
| 26-043 | Serie | 12.110008 | Flügelrad kpl. MTH3 Qn 1,5/2,5 PPS | 1508976 | Janz/ Nimoulda | Flügelrad Ø angepasst | Flügelrad Ø angepasst | SO00087546 – 8 Stk (LT 15.09.2026) SO00088760 – 1 Stk (LT 16.09.2026) SO00089061 – 1 Stk (LT 18.09.2026) | LKR
0
0
0
0
0
0
1
2
2
0
0
0
0
0
0

## Status Liste
Status
offen
freigegeben
abgeschlossen